## BOM_Normalized
Level | Parent Part Number | Part Number | Description | Qty | Revision | Supplier | ECO Ref | Cost ($) | Lead Time (weeks)
0 |  | PN-0001 | Echo Smart Display V2 | 1 | A | Amazon Lab126 |  | 0 | 0
1 | PN-0001 | PN-1000 | Display Assembly | 1 | A | LG Display |  | 0 | 0
1 | PN-0001 | PN-2000 | Main PCB Assembly | 1 | A | Pegatron |  | 0 | 0
1 | PN-0001 | PN-3000 | Housing Assembly | 1 | A | Foxconn |  | 0 | 0
1 | PN-0001 | PN-4000 | Battery Pack | 1 | A | Panasonic |  | 0 | 0
1 | PN-0001 | PN-5000 | Packaging Assembly | 1 | A | International Paper |  | 0 | 0
2 | PN-1000 | PN-1001 | 7-inch Display Panel | 1 | A | LG Display | ECO-01 | 18 | 6
2 | PN-1000 | PN-1002 | Touch Glass Digitizer | 1 | A | Corning | ECO-01 | 9 | 5
2 | PN-1000 | PN-1003 | Bezel Frame | 1 | A | Foxconn | ECO-01 | 2.5 | 4
2 | PN-2000 | PN-2001 | PCB Bare Board | 1 | A | Pegatron | ECO-03 | 22 | 8
2 | PN-2000 | PN-2002 | Wi-Fi Module | 1 | A | Murata | ECO-03 | 1.5 | 4
2 | PN-2000 | PN-2003 | Bluetooth Module | 1 | A | Qualcomm | ECO-03 | 6 | 6
2 | PN-2000 | PN-2004 | Power IC | 1 | A | TI | ECO-03 | 2 | 6
2 | PN-4000 | PN-4001 | Li-Ion Cell | 1 | A | Panasonic | ECO-04 | 8 | 7
2 | PN-4000 | PN-4002 | Protection PCB | 1 | A | Pegatron | ECO-04 | 3.5 | 5

## ECOs
ECO Number | Affected Part | Change Required | Reason | Impacted Build
ECO-01 | PN-1001, PN-1002, PN-1003 | Bezel thickness 2.0→2.5mm | Reduce warping | EVT→DVT
ECO-02 | PN-3000 | Switch housing to PC+ABS | Improve drop resistance | EVT→DVT
ECO-03 | PN-2001-2004 | PCB RevB + connector | Support new display | EVT→DVT
ECO-04 | PN-4001, PN-4002 | Battery 4000→4500mAh | Increase battery life | EVT→DVT

## Build Matrix
Build Phase | Units Planned | BOM Revision | ECOs Incorporated | Allocation Notes | Status
EVT | 20 | Rev A | None | Design, Reliability | Completed
DVT | 50 | Rev B | ECO-01,02,03 | Compliance, Accessory | In Progress
PVT | 200 | Rev C | All ECOs | Pilot, Demo | Planned

## PO Tracker
PO Number | Supplier | Part Number | Quantity | Order Date | Delivery Date | Status
PO-1001 | LG Display | PN-1001 | 100 | 2025-01-05 | 2025-02-15 | Shipped
PO-1002 | Foxconn | PN-3000 | 200 | 2025-01-10 | 2025-02-20 | In Production
PO-1003 | Panasonic | PN-4001 | 150 | 2025-01-12 | 2025-02-25 | Pending

## Risk Register
Risk ID | Description | Impact | Likelihood | Mitigation Plan | Owner
R-01 | Display delay risk | High | Medium | Dual sourcing | SCM
R-02 | Housing resin constraint | Medium | High | Qualify backup | OPS
R-03 | Battery overheating | High | Low | Thermal redesign | ENG

## Supplier Master
Supplier | Region | Preferred
LG Display | APAC | Yes
Pegatron | APAC | Yes
Foxconn | APAC | Yes
Panasonic | APAC | Yes
Corning | APAC | No
Murata | APAC | Yes
Qualcomm | APAC | No
TI | APAC | Yes
International Paper | APAC | Yes
Amazon Lab126 | APAC | Yes